## Sheet1
Sprint | User Story | Acceptance Criteria | Status
Sprint 0 Goal | Defining Problem Statement and decide to setup tools for Application Build
0 | As a developer, I want to set up the environment and tools so that the team can start working on the application. | The development environment is set up (including frontend and backend environments, Python, Flask, ML models) and setup repository for the team to collaborate. | Completed
Sprint 1 Goal | Backend Setup, User Management, and Frontend Framework
1 | As a user, I want to be able to sign up, log in, and manage my profile so that I can use the app to get personalized travel recommendations.
| 1.1: User Registration & Login | 1. Users can sign up using email or social login (Google, Facebook) 2. Users can log in to the platform. | Completed
| 1.2: Preference Setup | 1. Users can input budget, weather, and food preferences. 2. Data is saved in the user profile for future use. | Completed
1 | As a developer, I need a structured backend and frontend project to build future features upon.
| 1.3: Basic Destination Recommendation | 1. The platform suggests destinations based on user preferences. 2. Recommendations update if preferences change. | Completed
| 1.4 1: Database Setup | 1. A scalable database schema is designed and implemented. 2. User data is securely stored and retrievable. | Completed
Sprint 2 Goal | Travel Recommendation Engine and Frontend Integration
2 | As a user, I want to input my travel preferences (budget, weather, food) so I can get personalized travel recommendations. |  | Not Completed
2 | As a user, I want to see travel suggestions based on my preferences so I can plan my trip efficiently. |  | Not Completed
2 | As a developer, I need to integrate third-party APIs to fetch real-time data for travel recommendations (weather, pricing, etc.). |  | Not Completed
Sprint 3 Goal | User Dashboard, Advanced Features, and MVP Completion
3 | As a user, I want to view my past travel recommendations so I can easily access previous suggestions. |  | Not Completed
3 | As a user, I want to track my travel budget to ensure I stay within my financial limits. |  | Not Completed
3 | As a user, I want a seamless and mobile-responsive interface for ease of use on different devices. |  | Not Completed
3 | As a developer, I need to ensure the system is optimized and ready for deployment. |  | Not Completed