## Sprint 2
Sprint 2
ID | User Story/Technical Story | Description | Acceptance Criteria | Status | Comment
US 2.1 | User Story: Real-Time Weather Integration | As a traveler, I want real-time weather data for my destination recommendations. | 1. Platform integrates weather APIs to provide real-time weather data. 2. Destination suggestions are filtered by user-preferred weather conditions | completed
US 2.2 | User Story: Budget-Friendly Destination Suggestions | As a budget-conscious traveler, I want to see destination suggestions based on real-time pricing for flights and accommodations. | 1. Platform provides destination suggestions based on real-time flight pricing . 2. Platform provides destination suggestions based on real-time accommodation pricing. 3. Recommendations adjust according to the user's budget input. | Not completed | Some test cases failed due to destinations and accommodations exceeding budget limits; this story will carry over to the next sprint for further work.
TS 2.1 | Technical Story: Weather API Integration | Integrate weather API to fetch and filter real-time weather data for destinations. | 1. Weather data fetched in real-time. 2. Filter destinations by user-preferred weather conditions. | completed
TS 2.2 | Technical Story: Real-Time Price Data Integration | Integrate flight and accommodation APIs to pull real-time price data for destinations. | 1. Real-time flight and accommodation prices fetched. 2. Budget-adjusted recommendations served. | completed